## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: CARAGA 13 |  |  | CALENDAR YEAR: 2023
PROVINCE: SURIGAO DEL NORTE |  |  | QUARTER: 1
CITY/MUNICIPALITY: SURIGAO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Land:
Lot Acquisition for Barangay Relocation Site in Brgy. Balibayon | Brgy. Balibayon | 1223535.38 | Jan. 2023 |  | 0%
Total Land |  | 1223535.38
Water Supply:
Construction of Water System, Phase 1 | Brgy. Day-asan | 1450000 | Jan. 2023 |  | 0%
Construction of Water System, Phase 1 | Brgy. Buenavista | 1450000 | Jan. 2023 |  | 0%
Construction of Water System, Phase 1 | Brgy. Libuac | 1450000 | Jan. 2023 |  | 0%
Construction of Water System, Phase 1 | Brgy. Alang-Alang | 1450000 | Jan. 2023 |  | 0%
Construction of Water System, Phase 1 | Brgy. Catadman | 829000 | Jan. 2023 |  | 0%
Construction of Water System, Phase 1 | Brgy. Baybay | 1450000 | Jan. 2023 |  | 0%
Construction of Water System, Phase 1 | Brgy. Cantiasay | 1450000 | Jan. 2023 |  | 0%
Construction of Water System, Phase 1 | Brgy. San Jose | 1400000 | Jan. 2023 |  | 0%
Construction of Water System, Phase 1 | Brgy. Manjagao | 1450000 | Jan. 2023 |  | 0%
Construction of Water System, Phase 1 | Brgy. Bitaugan | 1400000 | Jan. 2023 |  | 0%
Construction of Water System, Phase 1 | Brgy. Aurora | 1450000 | Jan. 2023 |  | 0%
Total Water Supply |  | 15229000
Power Supply Systems:
Installation of Solar Street Lights | Brgy. Rizal | 3450000 | Jan. 2023 |  | 0%
Installation of Solar Street Lights | Brgy. Cagniog | 1380000 | Jan. 2023 |  | 0%
Installation of Solar Street Lights | Brgy. Sukailang | 1380000 | Jan. 2023 |  | 0%
Total Power Supply Systems |  | 6210000
School Buildings:
Construction of Daycare Center, Phase 1 | Brgy. Danawan | 1380000 | Jan. 2023 |  | 0%
Total School Buildings |  | 1380000
Hospital and Health Center:
Construction of Barangay Health Center, Phase 1 | Brgy. Rizal | 3450000 | Jan. 2023 |  | 0%
Construction of Barangay Health Center, Phase 1 | Brgy. Punta Bilar | 1380000 | Jan. 2023 |  | 0%
Rehabilitation of Birthing Facility, Phase 1 | Brgy. Sidlakan | 1380000 | Jan. 2023 |  | 0%
Rehabilitation of Health Center, Phase 1 | Brgy. Sugbay | 1380000 | Jan. 2023 |  | 0%
Total Hospital and Health Center |  | 7590000
Other Structures:
Rehabilitation of Evacuation Center, Phase 1 | Brgy. Alegria | 1380000 | Jan. 2023 |  | 0%
Rehabilitation of Covered Court/Evacuation Center, Phase 1 | Brgy. Bilabid | 1380000 | Jan. 2023 |  | 0%
Rehabilitation of Multi-Purpose Gym, Phase 1 | Brgy. Talisay | 1380000 | Jan. 2023 |  | 0%
Rehabilitation of Covered Court/Evacuation Center, Phase 1 | Brgy. Nonoc | 1380000 | Jan. 2023 |  | 0%
Rehabilitation of Covered Court/Evacuation Center, Phase 1 | Brgy. San Pedro | 1380000 | Jan. 2023 |  | 0%
Total Other Structures |  | 6900000
Information and Communication Technology Equipment:
Installation of Closed Circuit Television (CCTV) |  | 1311000 | Jan. 2023 |  | 0%
Total Information and Communication Technology Equipment |  | 1311000
TOTAL SOCIAL DEVELOPMENT PROJECTS |  | 39843535.38
ECONOMIC DEVELOPMENT
Agricultural Development:
Construction of Breeder Farm | Brgy. Mabini | 3450000 | Jan. 2023 |  | 0%
Total Agricultural Development |  | 3450000
Tourism Development:
Improvement of Luneta nan Surigao, Phase 1 | Brgy. Washington | 3360345.68 | Jan. 2023 |  | 0%
Total Tourism Development |  | 3360345.68
Other Development Projects:
Road Networks
Construction of Cagniog (CASETTA) - Luna (Bernadette Area Equipment)Road | Brgys. Cagniog to Luna | 10350000 | Jan. 2023 |  | 0%
Improvement of NRJ Balibayon - Sitio Tunga-Tunga - Silop Road | Brgys. Balibayon to Silop | 3450000 | Jan. 2023 |  | 0%
Improvement of File - Pinaypayan - Brazil Road | Brgy. Mat-i | 10350000 | Jan. 2023 |  | 0%
Construction of Danao - Mat-I road, Phase 1 | Brgy. Mat-i | 3450000 | Jan. 2023 |  | 0%
Construction of Gonzales Bridge, Phase 1 | Brgy. Washington | 17250000 | Jan. 2023 |  | 0%
Construction of Road at Purok Perlas including Drainage | Brgy. Taft | 3450000 | Jan. 2023 |  | 0%
Rehabilitation/Reconstruction of Road including Drainage, Phase 1 | Brgy. Washington | 3450000 | Jan. 2023 |  | 0%
Concreting of P. Quinto Street, Phase 1 | Brgy. San Juan | 2760000 | Jan. 2023 |  | 0%
Construction of Cagniog-Luna Bus Terminal Road, Phase 1 | Brgy. Luna | 3450000 | Jan. 2023 |  | 0%
Concreting of Road from Purok 1 to Purok 2, Phase 1 | Brgy. Canlanipa | 2070000 | Jan. 2023 |  | 0%
Concreting of Villamon Road, Phase 1 | Sitio Villamon, Brgy. Nabago | 1380000 | Jan. 2023 |  | 0%
Concreting of Purok 2 to Relocation Site, Phase 2 | Brgy. Orok | 1380000 | Jan. 2023 |  | 0%
Concreting of Purok 1 and 2 Road, Phase 1 | Brgy. San Roque | 1380000 | Jan. 2023 |  | 0%
Construction of Hanging/Foot Bridge at Sitio Panggabuon, Phase 1 | Brgy. Bonifacio | 1380000 | Jan. 2023 |  | 0%
Total Other Development Projects |  | 65550000
Loan Amortization:
LBP - Construction of 3rd Floor Existing Commercial Building |  | 436340.98 | Jan. 2023 |  | 28.47% | 124224.58
LBP - Acquiisition of Heavy Equipment |  | 27403475.88 | Jan. 2023 |  | 26.95% | 7385977.12
DBP - Finance Various Projects |  | 39967368.28 | Jan. 2023 |  | 0%
Total Loan Amortization |  | 67807185.14 | Jan. 2023 |  |  | 7510201.7
TOTAL ECONOMIC DEVELOPMENT |  | 140167530.82 | Jan. 2023 |  |  | 7510201.7
Jan. 2023
ENVIRONMENTAL MANAGEMENT |  |  | Jan. 2023
Flood Control System: |  |  | Jan. 2023
Rehabilitation/Upgrading of Drainage along the Streets of Vasquez - Rizal -Gimena - Gonzales to Surigao River | Brgy. Washington | 7659000 | Jan. 2023 |  | 0%
Construction of Seawall | Brgy. Sabang | 3450000 | Jan. 2023 |  | 0%
Rehabilitation of Seawall | Brgy. Talisay | 1400000 | Jan. 2023 |  | 0%
Total Flood Control System |  | 12509000
Other Structures:
Construction/Establishment of Cagniog Forest Park, Phase 1 | Brgy. Cagniog | 3450000 | Jan. 2023 |  | 0%
Total Other Structures |  | 3450000
TOTAL ENVIRONMENTAL MANAGEMENT |  | 15959000
GRAND TOTAL |  | 195970066.2 |  |  |  | 7510201.7
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
ATTY. JEFFREY P. GALIDO |  |  |  |  | PABLO YVES L. DUMLAO II
City Budget Officer |  |  |  |  | City Mayor

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1