## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION XIII - CARAGA |  | CALENDAR YEAR: | 2024
PROVINCE: | SURIGAO DEL NORTE |  | QUARTER: | 2
CITY/MUNICIPALITY: | CITY OF SURIGAO (Capital)
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT PROJECTS
Water Supply System:
Construction of Water System in Brgy. Day-asan Phase 2 | Brgy. Day-asan | 700000 | April 24, 2024 | July 22, 2024 | 0% | 0 |  | On-going
Construction of Water System in Brgy. Catadman Phase 2 | Brgy. Catadman | 1370850.94 | May 14, 2024 | July 12, 2024 | 0% | 0 |  | On-going
Construction of Water System in Brgy. Baybay Phase 2 | Brgy. Baybay | 1000000 |  |  | 0% | 0 |  | Awarded
Construction of Water System in Brgy. Bitaugan Phase 2 | Brgy. Bitaugan | 700000 | April 24, 2024 | July 22, 2024 | 0% | 0 |  | On-going
Construction of Water System in Brgy. San Jose Phase 2 | Brgy. San Jose | 700000 | June 13, 2024 | October 25, 2024 | 0% | 0 |  | On-going
Construction of Water System in Brgy.Alang-Alang Phase 2 | Brgy.Alang-Alang | 700000 | June 13, 2024 | October 5, 2024 | 0% | 0 |  | On-going
Construction of Water System in Brgy. Buenavista Phase 2 | Brgy. Buenavista | 700000 | June 21, 2024 | November 2, 2024 | 0% | 0 |  | On-going
Construction of Water System in Brgy. Libuac Phase 2 | Brgy. Libuac | 700000 | June 21, 2024 | November 2, 2024 | 0% | 0 |  | On-going
Construction of Water System in Brgy. Cantiasay Phase 2 | Brgy. Cantiasay | 700000 | June 13, 2024 | October 25, 2024 | 0% | 0 |  | On-going
Construction of Water System in Brgy. Aurora Phase 2 | Brgy. Aurora | 700000 |  |  | 0% | 0 |  | Awarded
Total Water Supply |  | 7970850.94 |  |  |  | 0
Buildings:
Reconstruction of Multi-Purpose Building, Phase 1 | Brgy. Alegria | 1000000 |  |  | 0% | 0 |  | Awarded
Construction/Completion of Panggaboon Multi-Purpose Building | Brgy. Bonifacio | 1000000 | June 17, 2024 | August 15, 2024 | 0% | 0 |  | On-going
Total Building |  | 2000000 |  |  |  | 0
School Building:
Completion of Daycare Center - Phase 2 | Brgy. Danawan | 500000 | July 2, 2024 | October 29, 2024 | 2.5% | 0 |  | On-going
Total School Buildings |  | 500000 |  |  |  | 0
Hospital and Health Center:
Construction of 2-3 Storey Barangay Health Center | Brgy. Taft | 15000000 | April 19, 2024 | January 13, 2025 | 0% | 0 |  | On-going
Total Hospital and Health Center |  | 15000000 |  |  |  | 0
Other Structures:
Rehabilitation of Covered Court/Evacuation Center, Brgy. Nonoc Phase 2 | Brgy. Nonoc | 1500000 | June 3, 2024 | August 31, 2024 | 10.3% | 0 |  | On-going
Rehabilitation of Multi-Purpose Gym, Brgy. Talisay Phase 2 | Brgy. Talisay | 500000 |  |  | 0% | 0 |  | On-going
Rehabilitation of Brgy. Covered Court, Phase 1, Brgy, Alang-Alang | Brgy. Alang-Alang | 2000000 | June 5, 2024 | August 3, 2024 | 10.1% | 0 |  | On-going
Rehabilitation of Multi-Purpose Gym, Brgy. Cantiasay | Brgy. Cantiasay | 1000000 |  |  | 0% | 0 |  | For bidding
Construction of Perimeter Fence in Brgy. Luna | Brgy. Luna | 5000000 |  |  | 0% | 0 |  | On-going
Total Other Structures |  | 10000000 |  |  |  | 0
TOTAL SOCIAL DEVELOPMENT PROJECTS |  | 35470850.94 |  |  |  | 0
ECONOMIC DEVELOPMENT PROJECTS
Other Development Projects:
Road Networks
Construction of Gonzales Bridge (Phase 2) | Brgy. Washington | 15000000 | June 17, 2024 | December 28, 2024 | 48% | 0 |  | On-going
Construction of Cantiasay-San Pedro Hanging Bridge (Phase 2) connecting Brgy. Cantiasay and San Pedro | Brgy. San Pedro | 10000000 |  |  | 0% | 0 |  | On-going POW and DED Plan
Construction of Sidewalks City Wide |  | 5500000 |  |  | 0% | 0 |  | On-going
Construction of Cagniog-Luna Bus Terminal Road, Brgy. Luna Phase 3, Brgy. Cagniog-Luna | Brgy, Cagniog--Luna | 4000000 | July 10, 2024 | September 22, 2024 | 0% | 0 |  | On-going
Road Concreting at Purok 7, Brgy. Sukailang | Brgy. Sukailang | 2500000 | July 4, 2024 | August 2, 2024 | 0% | 0 |  | On-going
Road Concreting of File-Pinaypayan-Brazil, Brgy. Mat-i | Brgy. Mat-i | 5000000 | June 3, 2024 | August 16, 2024 | 17% | 0 |  | On-going
Concreting of Roads towards Lipata National High School (Phase 2), Brgy. Lipata | Brgy. Lipata | 1000000 | July 4, 2024 | August 2, 2024 | 7% | 0 |  | On-going
Concreting of Access Road leading to Residential for Street Children, Bahay Pag-asa and DOH Drug Rehabilitation Center, Phase 1, Brgy. Anomar | Brgy. Anomar | 2400000 | June 14, 2024 | August 12, 2024 | 0% | 0 |  | On-going
Concreting of Pathway at Purok 4, Brgy. San Isidro | Brgy. San Isidro | 200000 |  |  | 0% | 0 |  | Awarded
Construction of Road and Promenade along Surigao River |  | 10000000 |  |  | 0% | 0 |  | Awarded
Construction of NRJ Trinidad-Mabini Farm-to-Market Road including Bridges (Equity) |  | 45000000 |  |  | 0% | 0 |  | Equity
Construction of 4-Lane Road in Pantalan 1, Surigao City |  | 10000000 | june 21, 2024 | October 3, 2024 | 0% | 0 |  | On-going
Concreting of Road in Purok Springville A, Sitio Payawan 2, Brgy. Luna | Brgy. Luna | 1000000 | July 2, 2024 | October 29, 2024 | 0% | 0 |  | On-going
Total Road Network |  | 111600000 |  |  |  | 0
Markets:
Construction of Mini-Public Market, Brgy. Taft (Phase 2) | Brgy. Taft | 5000000 | July 5, 2024 | November 1, 2024 | 0% | 0 |  | On-going
Construction of Mini-Public Market, Brgy. Rizal | Brgy. Rizal | 5000000 |  |  | 0% | 0 |  | Awarded
Total Markets |  | 10000000 |  |  |  | 0
Total Other Development Projects |  | 121600000 |  |  |  | 0
Loan Amortization:
LBP-Acquisitio of Heavy Equipment |  | 30730279.9 |  |  | 50.11% | 15400456.58
DBP-Construction of Swine Breeder Farm Facilities |  | 13083798.56 |  |  | 0%
Total Loan Amortization |  | 43814078.46 |  |  |  | 15400456.58
TOTAL ECONOMIC DEVELOPMENT PROJECTS |  | 165414078.46 |  |  |  | 15400456.58
ENVIRONMENTAL MANAGEMENT PROJECTS
Flood Control System:
Rehabilitation/Upgrading of Drainage along the Streets of Vasquez and Borja to Kinabutan River, Brgy. Washington | Brgy.Washington | 5000000 | June 21, 2024 | September 18, 2024 | 0% | 0 |  | On-going
Upgrading of Crossdrain from RCPC to RCBC at Sitio Lumaban, Brgy. Rizal | Brgy. Rizal | 1500000 | July 2, 2024 | August 30, 2024 | 0% | 0 |  | Awarded
Total Flood Control System |  | 6500000 |  |  |  | 0
TOTAL ENVIRONMENTAL MANAGEMENT PROJECTS |  | 6500000 |  |  |  | 0
GRAND TOTAL |  | 207384929.4 |  |  |  | 15400456.58
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| ATTY. JEFFREY P. GALIDO |  |  |  | PABLO YVES L. DUMLAO II
| City Budget Officer |  |  |  | City Mayor

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43