## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION XIII - CARAGA |  | CALENDAR YEAR: | 2023
PROVINCE: | SURIGAO DEL NORTE |  | QUARTER: | 4
CITY/MUNICIPALITY: | CITY OF SURIGAO (Capital)
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT PROJECTS
Land:
Lot Acquisition for Brgy. Site Expansion | Brgy. Serna | 2000000 | 2023-04-01 |  | 100% | 2000000 |  | Completed
Lot Acquisition for Brgy. Site Expansion | Brgy. Quezon | 11000000 | 2023-04-01 |  | 99.81% | 10979644.5
Lot Acquisitiion for Brgy. Heath Center | Brgy. Bilabid | 120000 | 2023-04-01 |  | 100% | 120000 |  | Completed
Lot Acquisition for New Public Cemetery Development |  | 5000000 | 2023-04-01 |  | 100% | 5000000 |  | Completed
Total Land |  | 18120000 |  |  |  | 18099644.5
Water Supply:
Construction of Water System in Brgy. Day-asan Phase 1 | Brgy. Day-asan | 1450000 | Sept. 11, 2023 | Nov. 10, 2023 | 100% | 1296417.15 |  | Completed
Construction of Water System in Brgy. Buenavista Phase 1 | Brgy. Buenavista | 1450000 | Aug. 17, 2023 | Dec. 14, 2023 | 90% | 1303512.37 |  | Ongoing
Construction of Water System in Brgy. Libuac Phase 1 | Brgy. Libuac | 1450000 | Aug. 23, 2023 | Jan. 19, 2024 | 90% | 1303802.86 |  | Ongoing
Construction of Water System in Brgy.Alang-Alang Phase 1 | Brgy.Alang-Alang | 1450000 | Aug. 23, 2023 | Jan. 19, 2024 | 90% | 1303551.6 |  | Ongoing
Construction of Water System in Brgy. Catadman Phase 1 | Brgy. Catadman | 829000 | Aug. 23, 2023 | Jan. 19, 2024 | 90% | 744897.2 |  | Ongoing
Construction of Water System in Brgy. Baybay Phase 1 | Brgy. Baybay | 1450000 | Aug. 23, 2023 | Jan. 20, 2024 | 90% | 1303605.09 |  | Ongoing
Construction of Water System in Brgy. Cantiasay Phase 1 | Brgy. Cantiasay | 1450000 | Aug. 25, 2023 | Jan. 22, 2024 | 90% | 1303041.36 |  | Ongoing
Construction of Water System in Brgy. San Jose Phase 1 | Brgy. San Jose | 1400000 | Sept. 4, 2023 | Dec. 23, 2023 | 90% | 1258705.02 |  | Ongoing
Construction of Water System in Brgy. Manjagao Phase 1 | Brgy. Manjagao | 1450000 | Aug. 17, 2023 | Dec. 14, 2023 | 90% | 1303455.86 |  | Ongoing
Construction of Water System in Brgy. Bitaugan Phase 1 | Brgy. Bitaugan | 1400000 | Sept. 4, 2023 | Dec. 23, 20223 | 90% | 1258810.34 |  | Ongoing
Construction of Water System in Brgy. Aurora Phase 1 | Brgy. Aurora | 1450000 | Aug. 25, 2023 | Dec. 22, 20223 | 90% | 1304675.86 |  | Ongoing
Construction of Water System | Brgy. San Isidro | 1500000 | Oct. 21, 2023 | Oct. 21, 2023 | 100% | 1347326.92 |  | Completed
Improvement of Water System at Purok 7 | Brgy. Balibayon | 60000 |  |  |  | 0 |  | for bidding
Total Water Supply |  | 16789000 |  |  |  | 15031801.63
Power Supply:
Installation of Solar Streets Lights | Brgy. Rizal | 3450000 | June 9, 2023 | Aug. 7, 2023 | 100% | 3093448.75 |  | Completed
Installation of Solar Streets Lights | Brgy. Cagniog | 1380000 | July 25, 2023 | Oct. 2, 2023 | 100% | 1372167 |  | Completed
Installation of Solar Streets Lights | Brgy. Sukailang | 1380000 | July 25, 2023 | Oct. 2, 2023 | 100% | 1372167 |  | Completed
Total Power Supply |  | 6210000 |  |  |  | 5837782.75
School Buildings:
Construction of Day Care Center, Brgy. Danawan - Phase 1 | Brgy. Danawan | 1380000 | Aug. 24, 2023 | Feb. 4, 2024 | 100% | 1377975.69 |  | Completed
Total School Buildings |  | 1380000 |  |  |  | 1377975.69
Buildings:
Rehabilitation of Multi-Purpose Building | Brgy. Danawan | 600000 | June 5, 2023 | Aug. 7, 2023 | 100% | 537843.74 |  | Completed
Rehabilitation of Multi-Purpose Building | Brgy. Mabua | 2000000 | Oct. 31, 2023 | Oct. 2, 2023 | 100% | 1032148.19 |  | Ongoing
Rehabilitation of Multi-Purpose Building | Brgy. Libuac | 2000000 | Sept. 28, 2023 | Oct. 2, 2023 | 100% | 1999209.02 |  | Completed
Total Building |  | 4600000 |  |  |  | 3569200.95
Hospital and Health Center:
Construction of Barangay Health Center in Brgy. Rizal | Brgy. Rizal | 3450000 | Aug. 4, 2023 | Oct. 30, 2024 | 100% | 3101867.4 |  | Completed
Construction of Health Center, Brgy. Punta Bilar Phase 1 | Brgy. Punta Bilar | 1380000 | July 4, 2023 | Oct. 31, 2023 | 97% | 1235132.73 |  | Ongoing
Rehabilitation of Health Center, Brgy. Sugbay Phase 1 | Brgy. Sugbay | 1380000 | Nov. 13, 2023 | Feb. 10, 2024 | 67% | 882808.36 |  | Ongoing
Total Hospital and Health Center |  | 6210000 |  |  |  | 5219808.49
Other Structures:
Rehabilitation of Evacuation Center, Brgy. Alegria Phase 1 | Brgy. Alegria | 1380000 | Aug. 24, 2023 | Feb. 4, 2024 | 100% | 1378177.76 |  | Completed
Rehabilitation of Covered Court/Evacuation Center, Brgy. Bilabid Phase 1 | Brgy. Bilabid | 1380000 | Aug. 4, 2023 | Oct. 3, 2023 | 100% | 1378731.38 |  | Completed
Rehabilitation of Multi-Purpose Gym, Brgy. Talisay Phase 1 | Brgy. Talisay | 1380000 | Aug. 1, 2023 | Septe. 29, 2023 | 100% | 1240387.53 |  | Completed
Rehabilitation of Covered Court/Evacuation Center, Brgy. Nonoc Phase 1 | Brgy. Nonoc | 1380000 | Aug. 3, 2023 | Sept. 1, 2023 | 90% | 1240575.53 |  | Ongoing
Rehabilitation of Covered Court/Evacuation Center, Brgy. San Pedro Phase 1 | Brgy. San Pedro | 1380000 | July 21, 2023 | Nov. 18, 2023 | 100% | 1234421.52 |  | Completed
Rehabilitation of Flat Bed Drier | Brgy. Capalayan | 500000 | Aug. 21, 2023 | Nov. 18, 2023 | 100% | 499188.08 |  | Completed
Rehabilitation of Flat Bed Drier | Brgy. Serna | 500000 | Aug. 8, 2023 | Dec. 20, 2023 | 100% | 260309.3 |  | Completed
Construction of Flat Bed Drier | Brgy. Trinidad | 1000000 | Aug. 21, 2023 | Nov. 18, 2023 | 100% | 999012.09 |  | Completed
Rehabilitation of Candava Multi-Purpose Gym | Brgy. Washington | 1500000
Total Other Structures |  | 10400000 |  |  |  | 8230803.19
Markets:
Construction of Mini Public Market | Brgy. San Juan | 5000000 | Dec. 5, 2023 | Sept. 29, 2024 | 35% | 1689965 |  | Ongoing
Construction of Mini Public Market | Brgy. Taft | 5000000 | Oct. 30, 2023 | Aug. 24, 2024 | 50% | 2471388.87 |  | Ongoing
Total Markets |  | 10000000 |  |  |  | 4161353.87
Slaughterhouse:
Rehabilitation and Improvement of Surigao City Slaughterhouse | Brgy. Poctoy | 2000000 | [5 empty] | For bidding
Total Slaughterhouse |  | 2000000
Information and Communication Technology:
Installation of Closed-Circuit Television (CCTV) | Brgy. Lipata | 1311000 | [5 empty] | Post-qua
Total Information and Communication Technology |  | 1311000
TOTAL SOCIAL DEVELOPMENT PROJECTS |  | 77020000 |  |  |  | 61528371.07
ECONOMIC DEVELOPMENT PROJECTS
Agricultural Development:
Construction of Breeder Farm | Brgy. Mabini | 3450000 | 2023-01-01 |  |  |  |  | Bidded
Other Transportation Equipment
Purchase of Two (2) units Farm Tractor |  | 3400000 | Sept. 2023 | Dec. 2023 | 100% | 3300000 |  | Completed
Total Agricultural Development |  | 6850000 |  |  |  | 3300000
Tourism Development:
Improvement of Luneta nan Surigao, Brgy. Washington Phase 1 | Brgy. Washington | 3360345.68 | Aug. 23, 2023 | June 17, 2024 | 80% | 2626315.13 |  | Ongoing
Total Tourism Development |  | 3360345.68 |  |  |  | 2626315.13
Other Development Projects:
Road Networks
Improvement of NRJ Balibayon-Sitio Tunga Tunga-Silop road, Brgys. Balibayon-Silop |  | 3450000 | Aug. 3, 2023 | Oct. 22, 2024 | 30% | 1033964.33 |  | Ongoing
Improvement of File-Pinaypayan-Brazil Road, Mat-i | Brgy, Mat-i | 10350000 | Aug. 30, 2023 | Feb. 28, 2024 | 90% | 9289102.71 |  | Ongoing
Construction of Danao-Mat-I Road, Brgy. Danao Phase 1 | Brgy. Mat-i | 3450000 | Sept. 1, 2023 | Nov. 20, 2023 | 90% | 3103720.56 |  | Ongoing
Construction of Gonzales Bridge (Phase 1) | Brgy. Washington | 17250000 | Aug. 23, 2023 | March 16, 2024 | 88.45% | 15257591.76 |  | Ongoing
Construction of Road at Purok Perlas including Drainage in Brgy. Taft Phase 1 | Brgy. Taft | 3450000 | Oct. 1, 2023 | Nov. 29, 2023 | 32% | 1054920.52 |  | Ongoing
Construction of Road at Purok Perlas including Drainage in Brgy. Washington Phase 1 | Brgy. Washington | 3450000 | Sept. 21, 2023 | Nov. 20, 2023 | 90% | 3103775.65 |  | Ongoing
Concreting of P. Quinto Street, Brgy. San Juan Phase 1 | Brgy. San Juan | 2760000 | Sept. 11, 2023 | Nov. 10, 2023 | 100% | 2478383.53 |  | Completed
Construction of Cagniog-Luna Bus Terminal Road, Brgy. Luna Phase 1 | Brgy. Luna | 3450000 | Dec. 7, 2023 | Oct. 9, 2024 |  | 0 |  | Bidded
Concreting of Road from Purok 1 to Purok 2, Brgy. Canlanipa Phase 1 | Brgy. Canlanipa | 2070000 |  |  |  | 0 |  | Bidded
Concreting of Villamon Road, Sitio Villamon, Brgy. Nabago Phase 1 | Brgy. Mat-i | 1380000 | Aug. 7, 2023 | Sept. 16, 2023 | 100% | 1373919.03 |  | Completed
Concreting from Purok 2 to Relocation Site (Phase 2), Brgy. Orok Phase 1 | Brgy. Orok | 1380000 | Sept. 6, 2023 | Oct. 23, 2023 | 50% | 683392.88 |  | Ongoing
Concreting of Purok 1 and 2, Brgy, San Roque Phase 1 | San Roque | 1380000 |  |  |  | 0 |  | For bidding
Construction of Hanging/Footbridge at Sitio Panggabuon, Brgy. Bonifacio Phase 1 | Brgy. Bonifacio | 1380000 | Aug. 29, 2023 | Oct. 27, 2023 | 90% | 1238330.52 |  | Ongoing
Concreting of Road connecting Purok 3 and 4 | Brgy. Mapawa | 2000000 | Sept. 29, 2023 | Nov. 28, 2023 | 100% | 1998975.38 |  | Completed
Rehabilitation of Togonan Hanging Bridge | Brgy. Mabini | 500000 | Oct. 9, 2023 | Oct. 9, 2024 | 51% | 251093.24 |  | Ongoing
Construction of Cagniog-Lina Bus Terminal Road Phase 2, Brgy. Cagniog-Luna |  | 8133535.38 | 2023-04-01 |  |  | 0
Construction of Hanging/Footbridge at Sitio Panggabuon, Brgy. Bonifacio Phase 2 | Brgy. Bonifacio | 4000000 | 2023-04-01 |  |  | 0
Construction of Cantiasay-San Pedro Hanging Bridge connecting Brgy. Cantiasay and San Pedro | Brgy. Cantiasay and Brgy. San Pedro | 10000000
Total Raod Network |  | 79833535.38 |  |  |  | 40867170.11
Drainage System:
Flood Control
Construction of Drainage System | Brgy. Cabongbongan | 1500000 | Sept. 25, 2023 | Jan. 8, 2024 | 100% | 1499708.39 |  | Completed
Construction of Drainage System from Espina to Nueva-Punta Basin |  | 5000000 | [5 empty] | Bidded
Total Other Development Projects |  | 6500000 |  |  |  | 1499708.39
Loan Amortization:
LBP-Construction of 3rd Floor existing Commercial Building |  | 436340.98 | Jan. 2023 |  | 69.72% | 304230.36
LBP-Acquisition of Heavy Equipment |  | 32370844.16 | Jan. 2023 |  | 95.32% | 30854649.08
Total Loan Amortization |  | 32807185.14 |  |  |  | 31158879.44
TOTAL ECONOMIC DEVELOPMENT PROJECTS |  | 129351066.2 |  |  |  | 79452073.07
ENVIRONMENTAL MANAGEMENT PROJECTS
Flood Control System:
Rehabilitation/ Upgrading of Drainage along the Streets of Vasquez-Rizal Gimena-Gonzales to Surigao River | Brgy.Washington | 7659000 | Sept. 1, 2023 | Feb. 15, 2024 | 52% | 3972412.91 |  | Ongoing
Construction of Seawall | Brgy. Sabang | 3450000 | Nov. 3, 2023 | Nov. 30, 2023 | 100% | 3439497.12 |  | Completed
Rehabilitation of Seawall | Brgy. Talisay | 1400000 | Aug. 4, 2023 | Sept. 14, 2023 | 100% | 1398526.07 |  | Completed
Total Flood Control System |  | 12509000 |  |  |  | 8810436.1
Other Structures:
Construction/ Establishment of Cagniog Forest Park, Brgy. Cagniog Phase 1 | Brgy. Cagniog | 3450000 | Aug. 17, 2023 | Dec. 14, 2023 | 51% | 1726539.34 |  | Ongoing
Total Other Structures |  | 3450000 |  |  |  | 1726539.34
TOTAL ENVIRONMENTAL MANAGEMENT PROJECTS |  | 15959000 |  |  |  | 10536975.44
GRAND TOTAL |  | 222330066.2 |  |  |  | 151517419.58
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| ATTY. JEFFREY P. GALIDO |  |  |  | PABLO YVES L. DUMLAO II
| City Budget Officer |  |  |  | City Mayor

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43