## Form 6a -TFU
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: | CARAGA 13 |  | CALENDAR YEAR: | 2023
PROVINCE: | SURIGAO DEL NORTE |  | QUARTER: | 2
CITY/MUNICIPALITY: | SURIGAO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
PROVINCE OF SURIGAO DEL NORTE
Concreting of Bagong Silang | Brgy. Washington | 6000000 |  |  | 89.01% | 5340409.95 |  | on-going
Concreting of Access Road at Candava | Brgy. Washington | 4750000 |  |  | 99.96% | 4748037.41 |  | completed
Concreting of Access Road at the Bank of Taft National High School | Brgy. Taft | 8100000 |  |  | 0%
DEPARTMENT OF INTERIOR & LOCAL GOVERNMENT (DILG)
Proposed Surigao Park Revitalization Plan | Surigao City | 15240885 | 8/14/2020 |  | 99.92% | 15229050.66 |  | completed
Proposed Surigao Park Revitalization Plan (Phase II) | Surigao City | 20584745 | 11/16/2020 |  | 84.97% | 17489943.52 |  | on-going
Concreting of Access Road from National Highway to Sitio Villamon | Brgy. Nabago | 20000000 | 2020-11-03 |  | 30.7% | 6139214.9 |  | on-going
Surigao Riverbank Rehab/Reforestration of Brgy. Poctoy and Brgy. Sabang | Brgy. Sabang | 500000 | 1/19/2016 |  | 100% | 500000 |  | completed
Construction of Access Road from Villamon to Panalsalan | Brgy. Nabago | 9500000 | 3/23/2020 |  | 99.95% | 9495057.72 |  | completed
Upgrading of Farm to Market Road Connecting P-4 to P-2 (Phase I) | Brgy. Trinidad | 14000000 | 6/15/2021 |  | 100% | 13999812.95 |  | completed
Upgrading of Farm to Market Road from silop to Landfill (Phase I) | Brgy. Silop | 17000000 | 5/25/2021 |  | 100% | 17000000 |  | completed
Upgrading of Farm to Market Road from P-10 connecting Danao-Serna | Brgy. Serna | 15000000 | 6/15/2021 |  | 100% | 15000000 |  | completed
Upgrading of Farm to Market Road Brgy. Sukailang proper to Bry. Ima Boundary(Phase I) Brgy. Sukailang | Brgy. Sukailang | 16000000 | 6/15/2021 |  | 100% | 16000000 |  | completed
Upgrading of Farm toMarket Roadfrom P-2 to Brgy. Silop (Phase I) | Brgy. Mapawa | 10000000 | 6/15/2021 |  | 100% | 10000000 |  | completed
Upgrading of Farm to Market Road at Purok Avocado | Brgy. Quezon | 8000000 | 6/15/2021 |  | 100% | 8000000 |  | completed
Upgrading of Farm to Market Road at Purok Nangka | Brgy. Quezon | 4500000 | 6/15/2021 |  | 100% | 4500000 |  | completed
Upgrading of Farm to Market Road from P-7 to P-2 to Paraiso-Danao | Brgy. Mat-i | 7000000 | 6/15/2021 |  | 100% | 7000000 |  | completed
Improvement/Rehabilitation of Brgy. Health Center | Brgy. Mapawa | 3000000 | 6/15/2021 |  | 100% | 3000000 |  | completed
Construction of Level II Potable Water Supply | Brgy. Mapawa | 7000000 | 6/15/2021 |  | 100% | 7000000 |  | completed
Completion of Brgy. Health Center | Brgy. Silop | 1000000 | 6/15/2021 |  | 100% | 1000000 |  | completed
Upgrading of Farm to Market Road from Brgy. Site towards Brgy. Reclamation Site | Brgy. Anomar | 14000000 | 6/15/2021 |  | 100% | 14000000 |  | completed
Construction of 2-Storey Barangay Health Center | Brgy. Trinidad | 2000000 | 6/15/2021 |  | 100% | 2000000 |  | completed
Construction of Level II Potable Water Supply | Brgy. Capalayan | 10000000 | 6/15/2021 |  | 100% | 10000000 |  | completed
Construction of 2-Storey Barangay Health Center | Brgy. Capalayan | 5000000 | 6/15/2021 |  | 100% | 5000000 |  | completed
Installation of Streetlighting of Entire Barangay | Brgy. Mabini | 1500000 | 5/25/2021 |  | 100% | 1500000 |  | completed
Rehab./Expansion of Brgy. Health Center at P-2 Brgy. Site | Brgy. Mabini | 1300000 | 5/25/2021 |  | 100% | 1300000 |  | completed
Improvement of Potable Water Supply Level III | Brgy. Sukailang | 1000000 | 6/15/2021 |  | 100% | 1000000 |  | completed
Construction of Level III Potable Water System | Brgy. Anomar | 6000000 | 6/15/2021 |  | 100% | 6000000 |  | completed
Improvement of Potable Water Supply Level III | Brgy. Poctoy | 5000000 | 6/15/2021 |  | 100% | 5000000 |  | completed
Completion of 1-Storey Barangay Health Center, Purok Tambis | Brgy. Quezon | 1000000 | 6/15/2021 |  | 100% | 1000000 |  | completed
Construction of Level II Water Supply | Brgy. Quezon | 3500000 | 6/15/2021 |  | 100% | 3500000 |  | completed
Construction of Barangay Health Center | Brgy. Mat-i | 3000000 | 6/15/2021 |  | 100% | 3000000 |  | completed
Installation of Street Lights | Brgy. Mat-i | 3000000 | 6/15/2021 |  | 100% | 3000000 |  | completed
Improvement of Street Lights from P-1 to P-6 Farm to Market Road | Brgy. Mabua | 3000000 | 6/15/2021 |  | 100% | 3000000 |  | completed
Construction of 1-Storey School Building at Emerico Borja Elementary School | Brgy. Trinidad | 4000000 | 6/15/2021 |  | 100% | 4000000 |  | completed
Improvement of Level III Water System P-1 to P-6 | Brgy. Mabua | 2000000 | 6/15/2021 |  | 100% | 2000000 |  | completed
Construction of Brgy. Health Center | Brgy. Mabua | 2000000 | 6/15/2021 |  | 100% | 2000000 |  | completed
Construction of 3-unit Classroom (Grade 1-3) Storey School Building | Brgy. Sukailang | 3000000 | 6/15/2021 |  | 100% | 3000000 |  | completed
DEPARTMENT OF AGRICULTURE
Upgrading of City Slaughterhouse | Brgy. Poctoy | 1000000 | 2017-11-04 |  | 100% | 1000000 |  | completed
DEPARTMENT OF TRANSPORTATION AND COMMUNICATION (DOTC)
Surigao Airport Development Projects (1st & 2nd tranch) | Brgy. Luna | 57600000 | 3/14/16,11/11/16 |  | 95.3% | 54891931.59 |  | on-going
NATIONAL HOUSING AUTHORITY (NHA)
Surigao City Country Homes | Brgy. Cagniog | 12109329.9 | 6/6/14,11/15/16 |  | 100% | 12030291.44 |  | completed
DEPARTMENT OF HEALT DOH)
Health Facility Enhancement Program (HFEP) for City Government of Surigao (1st Tranche) |  | 10750000 | 6/15/2023
Meals and Accomodation and Transportation Benefits |  | 1001000 | 9/15/2020
TESDA
UAQTEA SCHOLARSHIP |  | 13683994.26 | 2018-12-11 |  | 95.16% | 13022031.05 |  | on-going
DSWD
Supplemental Feeding-SFP Fund Allocation for 12th cycle |  | 6544800 | 2022-02-09 |  | 99.95% | 6541224 |  | completed
DILG
Seal of Good Local Governance Incentives Fund (SGLG) |  | 7000000
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ATTY. JEFFREY O. GALIDO |  |  | EMMADEL V. LISONDRA, CPA |  |  | PABLO YVES L. DUMLAO II
City Budget Officer |  |  | Acting City Accountant |  |  | City Mayor

## Form 6b - TFU (hidden)
LOCAL GOVERNMENT SUPPORT FUND (Report on Fund Utilization and Status of Program/Project Implementation)
REGION: |  |  | CALENDAR YEAR:
PROVINCE: |  |  | QUARTER:
CITY/MUNICIPALITY: |  |  | OFFICE:
Amount
Fund Source | Date of Notice of Authority to Debit Account Issued | Type of Program/Project | Name Title of Program/Project | Specific Location | Mechanism/Mode of Implementation | Estimated Number of Beneficiaries | Received | Obligation | Disbursement | Estimated Completion (Month and Year) | Remarks on Program/Project Status
Certified Correct by: |  |  |  |  | Attested by:
The Local Finance Committee:
Local Chief Executive
City Budget Officer
City Treasurer
City Planning and Development Coordinator
Instructions:
1 | The report shall prepared by the LFC, in coordination with the other local officials concerned (local accountant on the allotment, obligation and disbursements;
local engineers in the status of infrastructure projects, as may be applicable.
2 | The fund source shall be based on the NADAI issued to the cities.
3 | The type of program/project shall be identified, consistent with the projects that may be implemented under the Circular.
4 | Amount received refers to the amount received by the city as its location. It is the amount the NADAI. Obligation refers to the total amount obligated by the
city as of reporting period. Disbursement refers to the total amount paid as of reporting period.
5 | The status of programs/projects refers to the percentage of physical completion or delivery of service as of reporting period.

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v1