## Form 6a -TFU
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: | REGION XIII - CARAGA |  | CALENDAR YEAR: | 2024
PROVINCE: | SURIGAO DEL NORTE |  | QUARTER: | 3
CITY/MUNICIPALITY: | CITY OF SURIGAO (Capital)
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Province of Surigao del Norte
Concreting of Access Road at the Back of Taft National High School | Brgy. Taft | 8100000 | 2022-02-02 |  | 0% | 0
Department of Interior and Local Government (DILG)
Construction of Farm to Market Road (Phase 2) | Brgy. Mapawa | 12000000 | 8/15/2024 | 2025-10-02 | 60.06% | 7206966.18 |  | on going
Department of Transportation and Communication (DOTC)
Surigao Airport Development Projects (1st tranche P10,800.00 and 2nd tranche P46,800.00) | Brgy. Luna | 57600000 | 2016-02-06 |  | 98.83% | 56925616.59 |  | on going
DEPARTMENT OF HEALTH (DOH)
Completion of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Ipil | 1000000 | 10/17/2023 | 2024-11-09 | 99.95% | 999526.84 |  | completed
Completion of Washington District Center (1st tranche P400,000.00, 2nd tranche P1,000,000.00 & 3rd tranche P600,000.00) | Brgy. Washington | 2000000 | 9/25/2023 | 12/23/2024 | 91.24% | 1824751.11 |  | on going
Const. of New Barangay Health Services (1st tranche P350,000.00, 2nd tranche P875,000.00 & 3rd tranche P525,000.00) | Brgy. Bilabid | 1750000 | 10/16/2023 | 2/27/2024 | 46.42% | 812387.31 |  | on going
Const. of New Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Bgry. Manjagao | 1000000 | 2023-03-06 | 10/31/2024 | 30.78% | 307835.38 |  | on going
Const. of New Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Serna | 1000000 | 6/23/2023 | 10/31/2024 | 30.02% | 300246.49 |  | on going
Rep. of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Aurora | 1000000 | 10/26/2023 | 2024-06-06 | 69.98% | 699819.59 |  | on going
Rep. of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Balibayon | 1000000 | 10/16/2023 | 12/24/2024 | 89.38% | 893798.74 |  | on going
Rep. of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Cagniog | 1000000 | 10/16/2024 | 12/24/2024 | 97.27% | 972663.19 |  | on going
Rep. of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Catadman | 1000000 | 10/26/2023 | 2024-06-06 | 90.4% | 904009.98 |  | on going
Rep. of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Rizal | 1000000 | 10/17/2023 | 2024-11-09 | 99.96% | 999565.96 |  | completed
Rep. of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. San Isidro | 1000000 | 2023-03-06 | 10/31/2024 | 30.18% | 301841.49 |  | on going
Rep. of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. San Jose | 1000000 | 10/16/2023 | 12/24/2024 | 91.25% | 912520.96 |  | on going
Rep. of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Talisay | 1000000 | 10/16/2023 | 3/14/2024 | 89.6% | 896012.67 |  | on going
Rep. of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Sukailang | 1000000 | 9/28/2023 | 5/24/2024 | 99.95% | 999498.99 |  | completed
Rep. of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Zaragosa | 1000000 | 10/26/2023 | 2024-06-06 | 90.51% | 905074.88 |  | on going
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy.Alegria | 1000000 | 9/25/2023 | 4/22/2024 | 90.56% | 905586.36 |  | on going
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Anomar | 1000000 | 9/25/2023 | 5/24/2024 | 99.95% | 999500 |  | completed
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Baybay | 1000000 | 10/16/2023 | 12/24/2024 | 90.6% | 905954.91 |  | on going
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Bitaugan | 1000000 | 10/16/2023 | 12/24/2024 | 91.97% | 919729.5 |  | on going
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Buenavista | 1000000 | 9/25/2023 | 4/22/2024 | 90.63% | 906299.98 |  | on going
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Cagutsan | 1000000 | 10/16/2023 | 12/24/2024 | 91.4% | 914046.4 |  | on going
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Danao | 1000000 | 10/17/2023 | 2024-11-09 | 99.93% | 999330.41 |  | completed
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Day-asan | 1000000 | 9/28/2023 | 5/24/2024 | 99.91% | 999138.71 |  | completed
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Lipata | 1000000 | 10/17/2023 | 2024-11-09 | 99.95% | 999533.94 |  | completed
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Lisondra | 1000000 | 10/26/2023 | 2024-06-06 | 70% | 699986.38 |  | on going
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Nabago | 1000000 | 9/28/2023 | 5/24/2024 | 99.95% | 999499.4 |  | completed
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Nonoc | 1000000 | 10/16/2023 | 3/14/2024 | 89% | 889980.45 |  | on going
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Poctoy | 1000000 | 10/17/2023 | 2024-11-09 | 99.95% | 999539.91 |  | completed
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Punta Bilar | 1000000 | 10/17/2023 | 2024-11-09 | 99.95% | 999516.72 |  | completed
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. Sabang | 1000000 | 9/25/2023 | 4/22/2024 | 69.99% | 699925 |  | on going
Upgrading of Barangay Health Services (1st tranche P200,000.00, 2nd tranche P500,000.00 & 3rd tranche P300,000.00) | Brgy. San Pedro | 1000000 | 10/16/2023 | 3/14/2024 | 89.62% | 896167.77 |  | on going
Upgrading of Luna District Health Center(1st, 2nd& 3rd tranche) | Brgy. Luna | 1500000 | 10/16/2023 | 2/27/2024 | 51.65% | 774730.67 |  | on going
Health Emergency Allowance (HEA) |  | 5232000 | 5/30/2024 | 6/30/2024 | 100% | 5232000 |  | completed
TESDA
UAQTEA Scholarship |  | 13683994.26 | 2018-12-11 |  | 95.16% | 13022031.05 |  | on going
DSWD
Supplemental Feeding - SFP Fund Allocation for 14th Cycle |  | 6498000 | 8/20/2024 | 12/31/2024 | 0% | 0
DEPARTMENT OF AGRICULTURE
Integrated National Swine Production Initiatives for Recovery and Expansion Program (INSPIRE) |  | 10000000 | 1/25/2024 | 5/23/2024 | 54.88% | 5487850.16 |  | on going
JAPAN GGP
Project Procurement of Mobile X-Ray System |  | 3724778.85 | 7/26/2024 | 9/23/2024 | 100% | 3724778.85 |  | completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
ATTY. JEFFREY P. GALIDO |  |  | JOCELYN E. MONTEROS, CPA |  |  | PABLO YVES L. DUMLAO II
Local Budget Officer |  |  | Local Accountant |  |  | City Mayor

## Form 6b - TFU (hidden)
LOCAL GOVERNMENT SUPPORT FUND (Report on Fund Utilization and Status of Program/Project Implementation)
REGION: |  |  | CALENDAR YEAR:
PROVINCE: |  |  | QUARTER:
CITY/MUNICIPALITY: |  |  | OFFICE:
Amount
Fund Source | Date of Notice of Authority to Debit Account Issued | Type of Program/Project | Name Title of Program/Project | Specific Location | Mechanism/Mode of Implementation | Estimated Number of Beneficiaries | Received | Obligation | Disbursement | Estimated Completion (Month and Year) | Remarks on Program/Project Status
Certified Correct by: |  |  |  |  | Attested by:
The Local Finance Committee:
Local Chief Executive
City Budget Officer
City Treasurer
City Planning and Development Coordinator
Instructions:
1 | The report shall prepared by the LFC, in coordination with the other local officials concerned (local accountant on the allotment, obligation and disbursements;
local engineers in the status of infrastructure projects, as may be applicable.
2 | The fund source shall be based on the NADAI issued to the cities.
3 | The type of program/project shall be identified, consistent with the projects that may be implemented under the Circular.
4 | Amount received refers to the amount received by the city as its location. It is the amount the NADAI. Obligation refers to the total amount obligated by the
city as of reporting period. Disbursement refers to the total amount paid as of reporting period.
5 | The status of programs/projects refers to the percentage of physical completion or delivery of service as of reporting period.

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
38